## Product Backlog Changes
ConnectSphere Product Backlog Change Record
Purpose |  |  | One reusable record for every Product Backlog, implementation and test change across all ConnectSphere User Stories.
How to use |  |  | Append new rows for US03, US04, US05, US06 and future stories. Never overwrite an earlier approved decision or test execution.
Approval rule |  |  | Keep backlog changes as Proposed until reviewed by the team or Product Owner. Record the actual updater and date only after approval.
Notion rule |  |  | Notion Updated remains No until the Product Backlog is actually changed. Preserve the original wording in this workbook.
Change ID | Story ID | Item Type | Original Notion Text | Evidence Source | Evidence Statement | Problem Found | Change Action | Revised Text | Reason | Classification | Notion Updated | Updated By | Updated Date | Status
US05-CHG-01 | US05 | User Story | As an Event Organiser, I want to save an incomplete event request as a draft so that I can complete it later. | Week 1 Customer Briefing - Draft Event Requests; Week 4 Project Instructions - Draft Event Requests | Week 1 permits saving before submission so incomplete information can be completed later. Week 4 requires saving an incomplete request before submission. | No conflict identified. The benefit wording overlaps US06 implementation but remains a valid US05 purpose. | Keep | As an Event Organiser, I want to save an incomplete event request as a draft so that I can complete it later. | The original User Story accurately states the supported user, capability and purpose. | No Change | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-02 | US05 | Acceptance Criterion 1 | Can save an event request at any point without completing all mandatory fields | Week 1 Customer Briefing - Draft Event Requests and Typical Process Step 1; Week 4 Project Instructions - Draft Event Requests | The organiser can save an incomplete request before submission and may save and continue editing before submission. | At any point is broader than the source. Mandatory fields assumes a confirmed field list that the supplied evidence does not provide. | Rewrite | The Event Organiser can save an incomplete event request as a draft before submission. | Keeps the explicit incomplete-before-submission behaviour without inventing an unlimited trigger or mandatory-field list. | Correction | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-03 | US05 | Acceptance Criterion 2 | Has the draft stored with status "Draft" and a last-modified timestamp | Week 4 Project Instructions - Draft Event Requests | Draft requests should remain distinguishable from requests already submitted for review. | Draft status is supported. A last-modified timestamp is not explicitly required as a US05 customer outcome. | Rewrite | The saved event request has status "Draft" and remains distinguishable from a submitted event request. | Preserves the required status distinction. updated_at may remain a technical field but is not presented as a sourced US05 AC. | Correction | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-04 | US05 | Acceptance Criterion 3 | Has the draft visible only to themselves | Week 4 Project Instructions - User Authorisation and Authentication; Notion US02 and US06 | Access depends on role and relationship to an event. US06 separately governs viewing and editing one's own drafts. | Creator-only visibility is more specific than the Release 1 wording and duplicates the access/edit boundary already assigned to US02 and US06. | Remove from US05 | Removed from US05 Acceptance Criteria. Enforce authorised access through US02 and test own-draft viewing/editing under US06. | Avoids claiming an unsupported US05 permission while preserving server-side authorisation as a separate requirement. | Scope Correction | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-05 | US05 | Acceptance Criterion 4 | Cannot submit a draft until all mandatory fields are complete | Week 4 Project Instructions - Event Request Creation and Draft Event Requests; current section clarification | The documents require an incomplete draft to be saveable. They do not identify a complete binding mandatory-field list for submission in the evidence available here. | The criterion assumes a confirmed mandatory-field list and concerns submission validation, which belongs to US03/US04 rather than saving a draft. | Move out of US05 | Removed from US05. Submission blocking must be handled under US03/US04 only where exact mandatory requirements are evidenced. | Separates draft persistence from submission validation and prevents unsupported validation rules. | Scope Correction | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-06 | US05 | Acceptance Criterion 5 | Does not lose entered data when the browser session ends unexpectedly | Week 1 Customer Briefing - Draft Event Requests; Week 4 Project Instructions - Draft Event Requests | Saved incomplete information must remain available so the request can be completed or reviewed later. | Unexpected browser-session wording implies recovery of unsaved data, autosave or crash recovery, none of which is explicitly required. | Rewrite | The saved draft retains the event information explicitly saved by the Event Organiser. | Requires persistence of saved data without inventing autosave or recovery of unsaved browser state. | Correction | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US05-CHG-07 | US05/US06 | Scope Boundary | User Story purpose: so that I can complete it later; Week 4: return to it later and continue editing it | Week 4 Project Instructions - Draft Event Requests; original Notion US06 | Release 1 requires the combined draft workflow to support returning later and continuing editing. | Adding reopen/edit as another US05 AC would duplicate US06, whose title and AC already own reopening and editing a saved draft. | Keep in US06 | US05 persists the draft and saved values; US06 verifies listing, reopening, restoring and editing the saved draft. | Maintains end-to-end traceability while keeping Story responsibilities small and non-duplicative. | Clarification | Yes | Wen Yuetong (via Codex) | 2026-10-10 | Completed
US06-CHG-01 | US06 | Acceptance Criterion 1 | Can view a list of their own draft requests with last-modified dates | Week 4 Project Instructions (2).docx — Draft Event Requests | Event Organisers can save an incomplete event request before submission, return to it later, and continue editing it. | Last-modified dates are not required as a customer outcome. | Rewrite | The Event Organiser can access their saved draft requests to return to them later. | A list is the current UI implementation choice; timestamps are not an AC. | Correction | No |  |  | Proposed
US06-CHG-02 | US06 | Acceptance Criterion 2 | Can reopen a draft with all previously entered values restored | Week 4 Project Instructions (2).docx — Draft Event Requests | Event Organisers can save an incomplete event request before submission, return to it later, and continue editing it. | Previously entered could include unsaved data. | Rewrite | The Event Organiser can reopen a saved draft with all explicitly saved event information restored. | Limits restoration to persisted information. | Correction | No |  |  | Proposed
US06-CHG-03 | US06 | Acceptance Criterion 3 | Can edit, re-save, or delete a draft | Week 4 Project Instructions (2).docx — Draft Event Requests | Event Organisers can save an incomplete event request before submission, return to it later, and continue editing it. | Deletion has no written basis. Re-save should retain the same request identity. | Rewrite | The Event Organiser can edit and re-save the same draft before submission; the updated information replaces its previously saved information. | Supports continued editing without creating a duplicate draft. Deletion is excluded. | Correction | No |  |  | Proposed
US06-CHG-04 | US06 | Acceptance Criterion 4 | Can submit the draft once it is complete and valid | Week 4 Project Instructions (2).docx — Event Request Creation / Draft Event Requests | Event Organisers can create and submit event requests. Draft editing occurs before submission. | Submission and any evidenced validation are owned by US04. | Move out of US06 | Submission remains covered by US04 rather than duplicated as a US06 acceptance criterion. | Avoids importing the unsupported mandatory-field assumptions from the current submission code. | Scope Correction | No |  |  | Proposed
US06-CHG-05 | US06 | Acceptance Criterion 5 | Cannot view or edit drafts created by another user | Week 4 Project Instructions (2).docx — User Authorisation and Authentication | Users should only be able to view or modify information appropriate to their role and relationship to an event. | No contradiction for the organiser own-draft workflow. | Keep | The Event Organiser can access and edit only their own drafts. | Server uses authenticated organiser identity and limits operations to Draft status. | Explicit requirement | No |  |  | Proposed

## Implementation Changes
ConnectSphere Implementation Change Log
Change ID | Date | US/AC | Requirement Source | Evidence Statement | Evidence Classification | Change Type | File or DB Object | Before | After | Reason | Unit-Test Evidence | Integration-Test Evidence | Coverage Result | Execution Result | Status
US05-DOC-001 | 2026-10-10 | US05 Phase 0 | Week 7 Managing Changes Guide | Changes should update the Product Backlog and Acceptance Criteria with transparent evidence before implementation. | Explicit requirement | Documentation | docs/ConnectSphere_Change_Log.xlsx | No shared cross-story change record | Reusable three-sheet project change record created | Creates traceable backlog, implementation and execution evidence for every User Story. | Not started | Not started | Not measured | Workbook created and verified in Phase 0 | Completed
US05-BACKLOG-001 | 2026-10-10 | US05 | Week 1 Customer Briefing; Week 4 Project Instructions; Week 7 Guide to Managing Changes | US05 supports saving an incomplete event request before submission; the draft must remain distinguishable from a submitted request and retain explicitly saved event information. | Explicit requirement | Product Backlog | Notion: ConnectSphere Product Backlog / US05 | Five AC included unsupported details such as last-modified timestamp, owner-only visibility, mandatory-field submission rules and unexpected-session recovery. | Replaced with three evidence-supported AC covering save-before-submission, Draft status distinction and retention of explicitly saved information. | Aligns US05 with written evidence and keeps reopen/edit behavior in US06 and submission validation in US03/US04. | Not started | Not started | Not measured | Notion update verified by re-fetching the US05 section | Completed
US05-TEST-001 | 2026-10-10 | US05 AC1-AC3 | Approved Notion US05 Acceptance Criteria | Unit tests must demonstrate saving incomplete information, Draft status distinction and retention of explicitly saved information. | Explicit requirement | Unit Test (TDD Red) | tests/unit/event_request/test_us05_save_event_draft.py | No Python unit tests for US05 | Three readable unittest cases created before the business module | Establishes the expected US05 behaviour before implementation. | 3 tests executed; 3 errors because event_drafts does not yet exist | Not started | Not measured in Red phase | Expected TDD failure confirmed | Completed
US05-MOD-001 | 2026-10-10 | US05 AC1-AC3 | Approved Notion US05 Acceptance Criteria | Save incomplete information before submission; store Draft status; retain explicitly saved information. | Explicit requirement | Business Module (TDD Green) | backend/event_drafts.py → prepare_draft | No US05 Python business module | Pure function prepares a Draft payload with a copied draft_form. | Smallest module that satisfies the approved US05 acceptance criteria; it does not yet persist data or implement an API route. | 3/3 passed: tests/unit/event_request/test_us05_save_event_draft.py | Not started | 100% statement and branch coverage for backend/event_drafts.py | TDD Green confirmed | Completed
US05-API-001 | 2026-10-10 | US05 AC1-AC3 | Approved Notion US05; user instruction on authenticated organiser_id | Save a Draft before submission, retain saved information, and obtain organiser identity from the FastAPI authenticated session. | Explicit requirement | API and Persistence | backend/main.py; backend/models.py; backend/schemas.py | No Event SQLAlchemy model, draft request schema or authenticated draft route | POST /event-requests/drafts persists Draft using existing events table | Creates the confirmed FastAPI to SQLAlchemy boundary without adding a table or migration. | 3/3 event_drafts unit tests passed | 4/4 US05 FastAPI SQLAlchemy integration tests passed | event_drafts.py: 100% statement and branch | Completed | Completed
US05-TEST-002 | 2026-10-10 | US05 test environment | Project test execution requirement | Integration tests require the declared FastAPI TestClient and coverage dependencies in the local virtual environment. | Implementation decision | Test Environment | backend/requirements-test.txt; .venv | No repeatable test-dependency list | requirements-test.txt references app requirements plus coverage and httpx2 | Lets a team member reproduce US05 test and coverage commands without modifying application dependencies. | 146/146 project Unit Tests passed | 87/87 project Integration Tests passed | US05 module scoped only | Completed | Completed
US05-WEB-001 | 2026-10-10 | US05 AC1-AC3 | User instruction: Next.js calls FastAPI, never Supabase directly for private drafts | The Save as draft button must send the form to FastAPI through the existing same-origin /api proxy. | Explicit implementation constraint | Next.js API Integration | lib/app-context.tsx; lib/types.ts | Save as draft changed browser memory only | Save as draft calls /api/event-requests/drafts, then updates the prototype UI with the returned database id. | Keeps database authority on FastAPI and preserves HttpOnly session authentication. | Backend unit suite unchanged | FastAPI integration suite verifies endpoint behavior | Not applicable to UI adapter; US05 business module coverage remains 100% | Type check and Next.js build passed | Completed

## Test Executions
ConnectSphere Test Execution History
Test Case ID | Execution Record | Execution Type | Execution Command or Method | Environment | Actual Result | Status | Remarks | Executed By | Date of Execution | Evidence Location
US05-TC01 | 01 | Manual UI test | Organiser login → incomplete request → Save as Draft → Continue | Local Next.js / FastAPI / configured Supabase database | Wen reported successful save, Draft status, and retained name, description and attendance 80. | Pass | Reported by Wen. Continue then Save as Draft creates another draft; US06 review required. Time recorded as current Beijing time at user request. | Wen Yuetong | 2026-10-10 15:59 Asia/Shanghai | docs/US05_Test_and_DB_Record.docx — Execution Record 01